## Sheet1
INITIAL TIMELINE
TASK | DESCRIPTION | OWNER | DATES
1 | Project Kickoff | all | 2022-11-09
2 | Project Brainstorming | all | 11/09-11/16
3 | Project Information Due | all | 2022-11-16
4 | CHANGE IN PROJECT IDEA | all | 2022-11-30
5 | Revising Project Details | all | 2022-12-01
6 | Organize Documentation Files [Build Initial Timeline] | prakruti | 2022-12-02
7 | Learn/Teach Ourselves Webscraping | yidi, prakruti | 12/2-12/4
8 | Webscraping with Python + Python Output | yidi, prakruti | 12/4-12/6
9 | Brainstorm Algorithm Building | nashr, noura | 12/2-12/4
10 | Build C++ Algorithm + Output | nashr, noura | 12/4-12/6
11 | Link C++ and Python Components | all | 12/6-12/7
12 | Build Test Cases | noura | 2022-12-08
13 | Test Cases | noura | 2022-12-09
14 | Troubleshoot failed cases | all | 2022-12-10
15 | Video | all/unassigned | 2022-12-11
16 | Complete Documentation | prakruti | 2022-12-12