## Sheet1
REAL TIMELINE
TASK | DESCRIPTION | OWNER | DATES
1 | Project Kickoff | all | 2022-11-09
2 | Project Brainstorming | all | 11/09-11/16
3 | Project Information Due | all | 2022-11-16
4 | CHANGE IN PROJECT IDEA | all | 2022-11-30
5 | Revising Project Details | all | 2022-12-01
6 | Build Initial Timeline | prakruti | 2022-12-02
7 | Learn/Teach Ourselves Webscraping | yidi, prakruti, noura | 12/3-6/22
8 | Brainstorm Algorithm Building | noura, nash | 12/4-6/22
9 | Webscraping with Python | yidi, prakruti | 12/7-10/22
10 | Build C++ Ranking Algorithm | noura, nash | 12/9-10/22
11 | Link C++ and Python--FAILED/DID NOT WORK | noura | 12/10-11/22
12 | Simplify Webscrape Data + Run Test Cases | prakruti | 12/10-11/22
13 | Redo Ranking Algorithm in Python | noura, nash | 2022-12-11
14 | Build GUI in Python | yidi | 2002-12-12
15 | Build Test Cases | prakruti | 2002-12-12
16 | Run Test Cases | noura | 2022-12-12
17 | Troubleshoot from failed test cases | prakruti, noura, nash | 2022-12-12
18 | Video | prakruti, noura, nash | 2022-12-12
19 | Complete Documentation | prakruti, noura | 2022-12-12